## Sheet1
Engineering Project Contract Management Ledger
Serial Number | Number | Supplier | Signing Date | Contract Amount | Paid Amount | First Payment |  |  | Second Payment |  |  | Third Payment |  |  | Retention Money
[6 empty] | Payment Terms | Ratio | Amount | Payment Terms | Ratio | Amount | Payment Terms | Ratio | Amount | Ratio | Amount | Warranty Period
1 | BM8801 | Unit 1 | 20**/10/01 | 32000 |  | Payment after signing | 50% |  | After the goods arrive at the client's site | 40% |  | Installation completed, acceptance qualified, VAT invoice issued |  |  | 5% |  | One year
3 | BM8802 | Unit 2 | 20**/10/02 | 478867 |  | Payment after signing | 20% |  | Goods arrive on site and VAT invoice is issued. | 40% |  | Installation completed, acceptance qualified, VAT invoice issued |  |  | 2% |  | 6 months
4 | BM8803 | Unit 3 | 20**/10/03 |  |  | Payment after signing | 30% |  | More than 50% completed, passed acceptance inspection | 30% |  | Project completion, passed acceptance inspection |  |  | 5% |  | One year from the date of successful completion acceptance
6 | BM8804 | Unit 4 | 20**/10/04 | 440126.45 |  | Progress 50% acceptance passed | 50% |  | Project completion, passed acceptance inspection | 45% |  |  |  |  | 5% |  | One year from the date of successful completion acceptance
8 | BM8805 | Unit 5 | 20**/10/05 | 112658.44 |  | Complete 50% of the single unit work volume | 25% |  | Complete 80% of the individual work volume | 20% |  | This single engineering project is completed and accepted as qualified. |  |  | 5% |  | One year from the date of successful completion acceptance
10 | BM8806 | Unit 6 | 20**/10/06 | 7800 |  | Advance deposit after signing | 30% |  | Installation completed, passed acceptance inspection | 70%
12 | BM8807 | Unit 7 | 20**/10/08 |  |  | Payment after the goods arrive and pass inspection. | 100%
13 | BM8808 | Unit 8 | 20**/10/09 | 292556.71 |  | Within 10 working days after the contract is signed | 30% |  | Complete construction, pass acceptance inspection | 20% |  | All glass arrives at the site and passes acceptance inspection. |  |  | 10% |  | One year from the date of successful completion acceptance
14 | BM8809 | Unit 9 | 20**/10/10
15 | BM8810 | Unit 10 | 20**/10/11 | 560181.82 |  | Project completion, passed acceptance inspection | 95% | [7 empty] | 5% |  | One year from the date of successful completion acceptance
16 | BM8811 | Unit 11 | 20**/10/12 | 117735.8
17 | BM8812 | Unit 12 | 20**/10/13 | 183691.85
18 | BM8813 | Unit 13 | 20**/10/14 | 2600000 |  | Within 10 days before the project starts | 30% |  | 10 working days after the concealed project passes acceptance inspection | 30% |  | Within 10 working days after the main project is basically completed |  |  | 5% |  | One year
19 | BM8814 | Unit 14 | 20**/10/15 | 2080000 |  | Within 10 days before the project starts | 30% |  | Within 10 working days after the concealed project passes acceptance inspection | 30% |  | Within 10 working days after the main project is basically completed |  |  | 5% |  | One year
20 | BM8815