## Sheet1
Monthly Report on Engineering Quality Status
Reporting Unit: Guangxi Jiaxun Pipeline Engineering Co., Ltd. | [5 empty] | Record Time: |  |  | 2011.6.1
Engineering Project Name | Sub-project Name |  | Main inspection items | Inspection Ratio % |  | Number of inspections |  | Qualified quantity |  | First-time pass rate% | Final Pass Rate% |  | Monthly Quality Trends and Major Quality Issues
Unit Project Name | [5 empty] | (Unit) |  | (Unit)
1. Siyuan South Road: Pipeline crossing welding DN200-120m 2. Wuhua Avenue: Excavation backfill DN200-2620m Pipeline crossing welding DN200-140m Excavation pipeline welding DN200-2970m | Pipeline Engineering |  | Trench Excavation | 100 |  | 2620 |  | 2600 |  |  | 100 |  | The quality this month is excellent or above, with no major quality issues.
|  |  | Pipeline Welding | 100 |  | 3230 |  | 3230 |  |  | 100
Pipe Splicing and Repair
|  |  | Pipe trench backfilling | 100 |  | 2620 |  | 2620 |  |  | 100
|  |  | Pigging, blowing, and pressure testing | 100 |  | 140 |  | 140 |  |  | 100
| Crossing Project |  | Pipeline Welding | 100
|  |  | Pipe Splicing and Repair | 100
|  |  | Pipeline crossing in place | 100
|  |  | Pipeline pigging, purging, pressure testing | 100
| Cathodic Protection Engineering |  | Impressed Current Cathodic Protection | 100
|  |  | Sacrificial Anode Cathodic Protection | 100
| Station and Valve Room Engineering |  | Trench Excavation | 100
|  |  | Pipeline Installation | 100
|  |  | Pipeline Welding | 100
|  |  | Pipe Splicing and Repair | 100
|  |  | Pipe trench backfilling | 100
|  |  | Valve chamber installation and waterproofing | 100
|  |  | Buildings with a construction area less than 60 m² | 100
| Construction Engineering |  | Earthwork Engineering | 100
|  |  | Foundation Engineering | 100
|  |  | Cast-in-place Reinforced Concrete Main Structure Project | 100
|  |  | Masonry Work | 100
|  |  | Indoor preliminary decoration project | 100
|  |  | Window and Door Engineering | 100
|  |  | Roof Waterproofing Engineering | 100
|  |  | Indoor Water Supply and Drainage Pipeline Installation Project | 100
|  |  | Indoor electrical wiring installation project | 100
| Spherical Tank Engineering |  | Spherical Shell Plate Arrival Inspection and Non-Destructive Testing | 100
|  |  | Welding Material Delivery Inspection and Re-inspection | 100
|  |  | Sphere Tank Assembly Geometric Dimension Inspection | 100
|  |  | Sphere Tank Welding Quality Inspection | 100
|  |  | Spherical Tank Heat Treatment | 100
|  |  | Pressure Test | 100
|  |  | Foundation Settlement Observation | 100
|  |  | Painting and thermal insulation inspection | 100
|  |  | Ladder platform and accessories inspection | 100
| Yard Engineering |  | Trench Excavation | 100 | [6 empty] | 100
|  |  | Pipeline Welding | 100 | [6 empty] | 100
|  |  | Overhead pipe installation | 80 | [6 empty] | 100
Pipe Splicing and Repair
|  |  | Pipe trench backfilling | 100 | [6 empty] | 100
|  |  | Pigging, blowing, and pressure testing | 100 | [6 empty] | 100
| Household Engineering |  | Installation Quality Inspection | 45 | [6 empty] | 100
|  |  | Tightness Test Inspection | 100 | [6 empty] | 100
|  |  | Pipeline Anti-Corrosion Quality | 35 | [6 empty] | 100
Monthly Quality Evaluation Status of Unit Engineering Projects | Serial Number | Engineering Name and Unit Engineering Name |  |  | Construction area |  | Installation quantity |  | Unit Project Start and Completion |  |  | Quality Evaluation Grade |  | Evaluation Date | Remark
[5 empty] | （m2） |  | (10,000 yuan) |  | Time
|  | Siyuan South Road |  |  |  |  | 0.41 |  | Completed on 2011.05.26
|  | Wuhua Avenue |  |  |  |  | 23.21 |  | Start of construction: 2011.05.08
Prepared by: Liu Meitong Reviewed by: Zhao Haibo
Project Leader: Wang Libo Project Manager: Zhao Kaiqian

## Sheet2
Monthly Report on Engineering Quality Status
Reporting Unit: Chongqing Xiushan Longyang Construction Co., Ltd. | [5 empty] | Record Time: |  |  | 2012.6.30
Engineering Project Name | Sub-project Name |  | Main inspection items | Inspection Ratio % |  | Number of inspections |  | Qualified quantity |  | First-time pass rate% | Final Pass Rate% |  | Monthly Quality Trends and Major Quality Issues
Unit Project Name
Chongqing Xiushan Industrial Park 200,000 Square Meter Standard Workshop Building | 3# Building Supporting Warehouse 2 Foundation Bored Pile Project |  | Positioning Pile Re-line | 100 |  | 95 |  | 95 |  | 100 | 100 |  | The quality this month is excellent or above, with no major quality issues.
|  |  | Pile shaft reinforcement | 100 |  | 95 |  | 95 |  | 100 | 100
|  |  | Wall protection quality | 100 |  | 95 |  | 93 |  | 97 | 100
|  |  | Embedded rock | 100 |  | 95 |  | 90 |  | 94 | 100
|  |  | Core sampling | 100 |  | 95 |  | 95 |  | 100 | 100
| Crossing Project |  | Pipeline Welding | 100
|  |  | Pipe Splicing and Repair | 100
|  |  | Pipeline crossing in place | 100
|  |  | Pipeline pigging, purging, pressure testing | 100
| Cathodic Protection Engineering |  | Impressed Current Cathodic Protection | 100
|  |  | Sacrificial Anode Cathodic Protection | 100
| Station and Valve Room Engineering |  | Trench Excavation | 100
|  |  | Pipeline Installation | 100
|  |  | Pipeline Welding | 100
|  |  | Pipe Splicing and Repair | 100
|  |  | Pipe trench backfilling | 100
|  |  | Valve chamber installation and waterproofing | 100
|  |  | Buildings with a construction area less than 60 m² | 100
| Construction Engineering |  | Earthwork Engineering | 100
|  |  | Foundation Engineering | 100
|  |  | Cast-in-place Reinforced Concrete Main Structure Project | 100
|  |  | Masonry Work | 100
|  |  | Indoor preliminary decoration project | 100
|  |  | Window and Door Engineering | 100
|  |  | Roof Waterproofing Engineering | 100
|  |  | Indoor Water Supply and Drainage Pipeline Installation Project | 100
|  |  | Indoor electrical wiring installation project | 100
| Spherical Tank Engineering |  | Spherical Shell Plate Arrival Inspection and Non-Destructive Testing | 100
|  |  | Welding Material Delivery Inspection and Re-inspection | 100
|  |  | Sphere Tank Assembly Geometric Dimension Inspection | 100
|  |  | Sphere Tank Welding Quality Inspection | 100
|  |  | Spherical Tank Heat Treatment | 100
|  |  | Pressure Test | 100
|  |  | Foundation Settlement Observation | 100
|  |  | Painting and thermal insulation inspection | 100
|  |  | Ladder platform and accessories inspection | 100
| 11# Building, 6# Building, 10# Building, 8# Building Foundation Project |  | Wall protection quality | 100 |  | 288 |  | 268 |  | 91 | 100
|  |  | 8# Building, 11# Building, 6# Building Rock Embedment | 100 |  | 220 |  | 210 |  | 93 | 100
|  |  | 8# Building, 11# Building 6# Building Core Sampling | 10 |  | 220 |  | 220 |  | 100 | 100
|  |  | 8# Building, 10# Building Reinforcement Cage | 100 |  | 136 |  | 134 |  | 98 | 100
|  |  | 8# and 10# Building Pile Core Concrete Pouring | 100 |  | 136 |  | 136 |  | 100 | 100
Monthly Quality Evaluation Status of Unit Engineering Projects | Serial Number | Engineering Name and Unit Engineering Name |  |  | Construction area |  | Installation quantity |  | Unit Project Start and Completion |  |  | Quality Evaluation Grade |  | Evaluation Date | Remark
[5 empty] | （m2） |  | (10,000 yuan) |  | Time
| 1 | Chongqing Xiushan Industrial Park 200,000 Square Meter Standard Workshop
2
3
Prepared by: Reviewed by:
Project Leader: Project Manager: