## Big_Plan
MHPS (Huzhou) Co., Ltd.
Production Plan Table (Large)
Department: | Cell Manufacturing Department | [12 empty] | 2013 |  | Year | 11 | Month
Instruction | Customer | Product Name | Specification | Quantity (pcs) | Delivery Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | …… | 30 | 31
Item
123 | Microvast PACK | Pouch Cell | MV06203127NTP-10Ah | 10000 | 12.22 | Planned Production Quantity
124 | X | Pouch Cell | MV06203127NTP-6Ah | 5000 | 12.25 | Planned Production Quantity
Planned Production Quantity

## Mid-term_Plan
MHPS (Huzhou) Co., Ltd.
Mid-term Production Plan
Workshop: | Workshop 1 | [6 empty] | The |  | Week |  | Month |  | Day | to |  | Month |  | Day
Instruction | Customer | Product Name | Specification | Quantity (pcs) | Delivery Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | …… | 30 | 31
Item
123 | Microvast PACK | Pouch Cell | 10Ah | 10000 | 12.22 | Planned Production Quantity | 1: 5000; 2: 5000
[6 empty] | Actual Production Output | 1: 4850; 2: 5050
Ultra-short number
124 | X | Pouch Cell | 6Ah | 5000 | 12.25 | Planned Production Quantity | 3: 5000
[6 empty] | Actual Production Output | 3: 5000
[6 empty] | Ultra-short number | 3: 0

## Sheet1
xxx Company's Production Plan for March 19, 2012 - March 25, 2012
2012-03-18
Serial Number | Engineering Name | Project | Total Project Volume (T) | Quantity (pieces) | Quantity Completed This Month (T) | Material arrival status | March 12--March 18 Plan | Remark
1 | HuaZhi Plaza | TD22-25 Floor | 30 | 22 | 30 | All materials have arrived | All completed
|  | TD26-29 Floor | 90 | 54 | 90 | Part of the materials are missing | All completed
|  | QL4- D1, D2, B1 Steel Columns | 90 | 54 | 90 | Material plan has been submitted | Cutting and assembly completed, ready for riveting and assembly.
|  | QL4- D1, D2, B1 Steel Girders | 250 | 28 | 220 | All materials have arrived | All completed
|  | QL4- C3, C4 Steel Columns |  | 54 |  | All materials have arrived | All completed
|  | QL4- C3, C4 Steel Girders | 240 | 46 | 240 | All materials have arrived | All completed
|  | QL4- C3, C4 Steel Girders |  | 37 |  | All materials have arrived | C3 area completed, C4 area partially completed
2 | Fulin Metropolis | 2F Steel Column | 95 | 23 | 40 | Materials not complete | Start cutting and assembling, produce finished products according to the plan.
3 | Chuanqi New Energy Vehicle | Steel columns, steel beams | 330 | 330 | 60 | All materials have arrived | All completed
|  | Column support / Horizontal bracing / Tie rod | 30 | 20 | 30 | All materials have arrived | All cow legs, auxiliary beams, other components, and attachments have been completed.
|  | Crane Girders / Truss System | 150 | 96 |  | Materials not arrived | To be determined according to the material and arrangement situation
4 | Sichuan Jianhua Pipe Pile | B Workshop Crane Girders and Trusses | 130 | 110 | 90 | All materials have arrived | Truss Angle Steel Completed
|  | B Workshop Platform Beams, Columns |  | 20 |  | All materials have arrived | All completed
|  | Skylight frame, mixing building |  |  |  | All materials have arrived | Mixer Building Completed
|  | A and B Yard Crane Girders | 160 | 280 |  | All materials have arrived
|  | Truss and Support of Yards A and B | 113 |  | 50 | All materials have arrived | The remaining column spacing supports for the remaining part of lines 24-51 are completed.
5 | FAW-Volkswagen No.7 | Steel Columns and Beams | 260 |  | 260 | Part of the materials are missing
|  | Column supports, tie rods,隅撑 (bracing) | 30 |  | 30 | All materials have arrived | All column spacing supports and column top tie rods are completed.
6 | Jiannanchun | Crane Girders / Truss System | 275 | 220 | 220 | All materials have arrived | Start rivet welding in an interlaced manner
|  | 25-30 Axis Steel Frame | 30 | 78 |  | All materials have arrived
7 | Jiannanchun | Small workshop厂房 | 6 |  | 6 | All materials have arrived | Complete and dispatch before March 20th.
8 | Laforte | small steel column | 10 | 65 | 10 | All materials have arrived | H-beam and supplementary small steel columns production completed and dispatched.
Total