## Sheet28
Production Plan Table
Product Quantity 9 |  | Completed 1 |  | In Production 5 |  |  | Order Number |  | Order Quantity |  | Produced | Progress | Delivery Date
[7 empty] | 1235 |  | 1000 |  | 400 | 40% | 22/5/21
Customer Name | Order Number | Product Name | Specification | Order Quantity | Unit | Production Daily Production | Start Date | Estimated Completion | Produced Quantity | (Days) | Production Progress | Production Progress | Remaining Days | Responsible Person
Rice Hull | 123 | Phone case | individual | 2000 | individual | 500 | 5/11 | 5/16 | 2000 | 4 | 100% | May 20th | 1 | Mumu
Rice Hull | 1235 | Battery | individual | 1000 | individual | 400 | 5/15 | 5/18 | 400 | 2.5 | 40% | May 21st | 2 | Mumu
Rice Hull | 1236 | Phone case | individual | 800 | individual | 400 | 5/16 | 5/19 | 480 | 2 | 60% | May 21st | 2 | Mumu
Rice Hull | 1237 | Battery | individual | 700 | individual | 300 | 5/17 | 5/20 | 360 | 2.3 | 51% | May 22nd | 3 | Mumu
Rice Hull | 123 | Phone case | individual | 600 | individual | 230 | 5/18 | 5/2 | 300 | 2.6 | 50% | May 23rd | 4 | Mumu
Rice Hull | 1239 | Battery | individual | 504 | individual | 200 | 5/19 | 5/22 | 150 | 25 | 30% | May 24th | 5 | Mumu
Rice Hull | 1240 | Phone case | individual | 505 | individual | 150 | 5/20 | 5/24 |  | 3.4 | 0% | May 25th | 6 | Mumu
Rice Hull | 1241 | Battery | individual | 506 | individual | 150 | 5/21 | 5/25 |  | 3.4 | 0% | May 26th | 7 | Mumu
Rice Hull | 1242 | Phone case | individual | 507 | individual | 200 | 5/22 | 5/25 |  | 2.5 | 0% | May 27th | 8 | Mumu