## Work_Assignment_Table
Task Name | Resource Name | Work Hours Completion Percentage | Work hours | Unit
Land Expansion | Development Department | 0% | 2,176 hours | 100%
Regional Company Development Department Provides Intended Project Information to the Group | Development Department | 0% | 8 hours | 100%
Investment Analysis Results in the Land Stage | Development Department | 0% | 72 hours | 100%
1. Project Investment Proposal | Development Department | 0% | 40 hours | 100%
Market Research and Data Collection | Development Department | 0% | 24 hours | 100%
Prepare the report "Company Strategic Intent, Market Assumptions, and Customer Positioning" | Development Department | 0% | 40 hours | 100%
2. Project Preparatory Plan | Development Department | 0% | 40 hours | 100%
3. Project Investment Analysis Model (Land Version) | Development Department | 0% | 8 hours | 100%
PMO Meeting Review and Argumentation | PMO | 0% | 16 hours | 100%
Investment Committee Review | Development Department | 0% | 8 hours | 100%
Obtain the Letter of Award | Development Department | 0% | 0 hours | 100%
Project Company Registration | Administration Department | 0% | 776 hours | 100%
Prepare the materials required for the project company registration | Administration Department | 0% | 88 hours | 100%
Determine the project company's registered agent company and sign the contract | Administration Department | 0% | 80 hours | 100%
Register the project company and obtain the business license and official seal. | Administration Department | 0% | 448 hours | 100%
Complete foreign exchange settlement | Administration Department | 0% | 240 hours | 100%
Land Transfer Contract (including boundary survey, topographic mapping, etc.) | Development Department | 0% | 984 hours | 100%
Postponed signing of land transfer contract | Development Department | 0% | 264 hours | 100%
Understand the government's internal process and approval procedures for signing land transfer contracts in Shanghai. | Development Department | 0% | 40 hours | 100%
Understand the difficulties and key individuals to be addressed in public relations for the delayed signing of land transfer contracts. | Development Department | 0% | 40 hours | 100%
Conduct government relations to delay signing the land transfer contract | Development Department | 0% | 216 hours | 100%
Complete Demolition | Development Department | 0% | 264 hours | 100%
Confirm the completion time of demolition and relocation | Development Department | 0% | 64 hours | 100%
Urge the government and first-level development companies to complete demolition and relocation on time. | Development Department | 0% | 264 hours | 100%
Land Contract Signing | Development Department | 0% | 56 hours | 100%
Pay 10% of the land price | Finance Department | 0% | 8 hours | 100%
Pay the remaining 90% land price and all deed tax | Finance Department | 0% | 240 hours | 100%
Apply for the Construction Land Use Planning Permit | Development Department | 0% | 152 hours | 100%
Processing the Certificate of Approved Construction Land | Development Department | 0% | 88 hours | 100%
Obtain the topographic map of the land, planning boundary report, etc. | Development Department | 0% | 40 hours | 100%
Application Form for Construction Land Planning Permit | Development Department | 0% | 8 hours | 100%
Construction Land Use Planning Permit Approval | Development Department | 0% | 64 hours | 100%
Obtain the Construction Land Use Planning Permit | Development Department | 0% | 0 hours | 100%
Handle the State Land Use Right Certificate | Development Department | 0% | 360 hours | 100%
Data Preparation | Development Department | 0% | 240 hours | 100%
Prepare the Construction Land Approval Document | Development Department | 0% | 8 hours | 100%
Prepare Construction Land Use Planning Permit | Development Department | 0% | 8 hours | 100%
All land price payment certificates | Finance Department | 0% | 8 hours | 100%
Real Estate Transfer Tax Payment Voucher | Finance Department | 0% | 8 hours | 100%
Cadastral Map | Development Department | 0% | 8 hours | 100%
Land Certificate Application Form | Development Department | 0% | 8 hours | 100%
Land Use Right Certificate Approval | Development Department | 0% | 120 hours | 100%
1. Obtain the State Land Use Right Certificate | Development Department | 0% | 0 hours | 100%
2. Land handover (Development Department to Engineering Department) | Development Department | 0% | 80 hours | 100%
Development Department transfers project materials to the R&D Department (transaction confirmation letter, regional control plan materials, project planning conditions, meeting materials, etc.) | Development Department | 0% | 8 hours | 100%
Process bank loan | Finance Department | 0% | 672 hours | 100%
Prepare documents submission application (requires state land certificate, land use planning permit) | Finance Department | 0% | 56 hours | 100%
The bank accepts the application and entrusts the evaluation agency to assess the project; the company entrusts the land evaluation agency to assess the land. | Finance Department | 0% | 168 hours | 100%
Branch submits for approval to the provincial branch meeting | Finance Department | 0% | 168 hours | 100%
Low-density projects require submission for approval by the head office. | Finance Department | 0% | 112 hours | 100%
Sign the loan contract and handle the land mortgage registration | Finance Department | 0% | 112 hours | 100%
Down Loan (Four Certificates) | Finance Department | 0% | 56 hours | 100%
Project Initiation | Project Team | 0% | 360 hours | 100%
Build the project team | PMO | 0% | 360 hours | 100%
Establish the project department organizational structure | Project Leader | 0% | 240 hours | 100%
Establish engineering management system | Project Leader | 0% | 240 hours | 100%
Team Training | Project Team | 0% | 120 hours | 100%
Project Initiation Phase Outcomes | Project Team | 0% | 120 hours | 100%
4. Project Positioning Report | Marketing Department | 0% | 80 hours | 100%
Planning Scheme, Introduction of Planning Indicators | R&D Department | 0% | 16 hours | 100%
Product Requirements and Recommendations | Marketing Department | 0% | 64 hours | 100%
Recreational facilities, commercial areas, public areas, and residential configuration standards | Project Team | 0% | 48 hours | 100%
Rough-in Planning for Finishing (if applicable) | Marketing Department | 0% | 64 hours | 100%
The development and sales plan of the project | Project Team | 0% | 56 hours | 100%
5. "Project Primary and Secondary Schedule" | Project Leader | 0% | 80 hours | 100%
6. Cost Sensitivity Analysis, Value Allocation, and Target Cost Preset | Cost Department | 0% | 80 hours | 100%
Various Cost Forecast Analysis (Land Cost, Construction Cost, Period Expenses, Total Cost) | Cost Department | 0% | 80 hours | 100%
Cost Control Contingency Plan | Cost Department | 0% | 40 hours | 100%
Cost Control Key Points and Challenges | Cost Department | 0% | 40 hours | 100%
Determining river channel management, foundation treatment plan, and noise reduction plan | Engineering Department | 0% | 40 hours | 100%
7. "Clubhouse, Sales Office, Model Unit Site Selection, Positioning, and Opening Plan" | Marketing Department | 0% | 80 hours | 100%
Site sales office and model area location selection, area planning, functional zoning, interior and exterior styles, landscape, and other specific requirements | Marketing Department | 0% | 80 hours | 100%
Sales Gallery and Model Unit Opening Plan | Marketing Department | 0% | 80 hours | 100%
8. Investment Analysis Report (Initiation) | Finance Department | 0% | 80 hours | 100%
Sales Progress and Price Expectations in the Startup Phase | Finance Department | 0% | 80 hours | 100%
Calculation of the Preliminary Target Cost | Finance Department | 0% | 80 hours | 100%
9. "Design Proposal Brief" | R&D Department | 0% | 80 hours | 100%
10. "Landscape Design Brief" | R&D Department | 0% | 80 hours | 100%
11. "Luxury Housing Positioning, Price Limitation, and Construction Implementation Plan" (if applicable) | R&D Department | 0% | 80 hours | 100%
Convene Project Kick-off Meeting | PMO | 0% | 16 hours | 100%
Project Initiation Phase Deliverables Submitted for Group Approval | PMO Convenor | 0% | 24 hours | 100%
Planning and Design | R&D Department | 0% | 2,376 hours | 100%
Constructive Detailed Planning Design | R&D Department | 0% | 912 hours | 100%
Preparation Work | R&D Department | 0% | 264 hours | 100%
Project Market Preliminary Judgment, Preliminary Product Positioning | Marketing Department | 0% | 32 hours | 100%
Draft Conceptual Planning and Design Task Statement | R&D Department | 0% | 32 hours | 100%
Determine the participating conceptual planning and design units | R&D Department | 0% | 40 hours | 100%
Planning Conditions, Compilation and Editing of Reference Materials | R&D Department | 0% | 96 hours | 100%
Planning Conditions, Compilation and Editing of Reference Materials | Development Department | 0% | 96 hours | 100%
Concept Planning Phase Work Confirmation Letter Signing, Issuance of Task Letters and Related Materials | R&D Department | 0% | 8 hours | 100%
Draft Conceptual Planning and Design Contract and Approval | R&D Department | 0% | 64 hours | 100%
Draft Conceptual Planning and Design Contract and Approval | Cost Department | 0% | 64 hours | 100%
Conceptual Planning Work Process Management | R&D Department | 0% | 88 hours | 100%
Conceptual Planning Review, Determine the Detailed Planning Design Direction and the Overall Design Contractor for This Project | Project Team | 0% | 40 hours | 100%
Coordinate with relevant government departments and confirm the planning scheme development direction | Project Team | 0% | 32 hours | 100%
Obtain basic planning and design data (control plan, red line map, hydrological and geological data, etc.) | Development Department | 0% | 104 hours | 100%
Obtain basic planning and design data (control plan, red line map, hydrological and geological data, etc.) | R&D Department | 0% | 104 hours | 100%
Government Public Relations (Government approval allows submission of planning proposal for approval before signing the land transfer agreement) | Development Department | 0% | 104 hours | 100%
Government Public Relations (Government approval allows submission of planning proposal for approval before signing the land transfer agreement) | R&D Department | 0% | 104 hours | 100%
Draft the design general contracting contract (including detailed design, architectural plan, preliminary design, construction drawings, landscape, etc.) | R&D Department | 0% | 80 hours | 100%
Sign the design general contracting contract | R&D Department | 0% | 16 hours | 100%
Planning and Design Task Book, Scheme Design Task Book Internal Confirmation | Project Team | 0% | 96 hours | 100%
Project Market Positioning Report | Marketing Department | 0% | 8 hours | 100%
Issue the planning and design task book and the scheme design task book | R&D Department | 0% | 40 hours | 100%
Adjustment of Planning and Design Task Book (if necessary, depending on the communication with the government) | R&D Department | 0% | 40 hours | 100%
Complete the planning scheme design | R&D Department | 0% | 464 hours | 100%
Process management of detailed planning design work, internal confirmation of the plan (two regular meetings every Monday and Friday) | R&D Department | 0% | 168 hours | 100%
Communicate with government planning department (planning section) | R&D Department | 0% | 80 hours | 100%
Detailed Planning Approval | R&D Department | 0% | 96 hours | 100%
Sunlight Analysis | R&D Department | 0% | 96 hours | 100%
Consultation on Detailed Planning Scheme (Approximately 19 Government Departments) | R&D Department | 0% | 96 hours | 100%
Consultation on Detailed Planning Scheme (Approximately 19 Government Departments) | Engineering Department | 0% | 96 hours | 100%
Water Services | R&D Department | 0% | 96 hours | 100%
Water Services | Engineering Department | 0% | 96 hours | 100%
Power Supply | R&D Department | 0% | 96 hours | 100%
Power Supply | Engineering Department | 0% | 96 hours | 100%
Gas | R&D Department | 0% | 96 hours | 100%
Gas | Engineering Department | 0% | 96 hours | 100%
Fire protection | R&D Department | 0% | 96 hours | 100%
Fire protection | Engineering Department | 0% | 96 hours | 100%
Civil Air Defense | R&D Department | 0% | 96 hours | 100%
Civil Air Defense | Engineering Department | 0% | 96 hours | 100%
Traffic | R&D Department | 0% | 96 hours | 100%
Traffic | Engineering Department | 0% | 96 hours | 100%
Communications | R&D Department | 0% | 96 hours | 100%
Communications | Engineering Department | 0% | 96 hours | 100%
Greening | R&D Department | 0% | 96 hours | 100%
Greening | Engineering Department | 0% | 96 hours | 100%
Approval of River Landscape Renovation Plan | Engineering Department | 0% | 96 hours | 100%
Jiasong Highway Road Landscape Renovation Plan Approval Submission | Engineering Department | 0% | 96 hours | 100%
Sixth Avenue Landscape Renovation Plan Approval Submission | Engineering Department | 0% | 96 hours | 100%
Obtain the Notice of Planning Review Opinion | R&D Department | 0% | 160 hours | 100%
Feasibility Study Report Preparation | Development Department | 0% | 712 hours | 100%
Select the feasibility study preparation agency unit | Development Department | 0% | 96 hours | 100%
Project Proposal Preparation | Development Department | 0% | 280 hours | 100%
Feasibility Study Report Preparation | Development Department | 0% | 280 hours | 100%
Project Proposal Approval | Development Department | 0% | 80 hours | 100%
Feasibility Study Report Approval | Development Department | 0% | 80 hours | 100%
Handle project initiation and collect IC card | Engineering Department | 0% | 16 hours | 100%
Architectural Design Scheme | R&D Department | 0% | 512 hours | 100%
Adjustment and confirmation of the architectural design task book (if necessary) | R&D Department | 0% | 40 hours | 100%
Design work process management, scheme internal confirmation (two regular meetings every Monday and Friday) | R&D Department | 0% | 200 hours | 100%
Communicate with government planning departments (Construction Management Section) | R&D Department | 0% | 56 hours | 100%
Architectural Plan Approval | R&D Department | 0% | 120 hours | 100%
Preliminary Design Calculation and Preliminary Design Guidance | Project Team | 0% | 512 hours | 100%
12. "Scheme Design Results" | R&D Department | 0% | 40 hours | 100%
13. "Guidelines for Coordination between Landscape and Architectural Schemes" | R&D | 0% | 40 hours | 100%
14. "Guidelines for Coordination between Finishing House Plan and Architectural Plan" (if any) | R&D Department | 0% | 40 hours | 100%
15. Cost Estimation and Verification | Cost Department | 0% | 160 hours | 100%
Completion of Product Configuration Standards in the Scheme Phase | Marketing Department | 0% | 8 hours | 100%
Scheme Phase Internal Discussion | Project Team | 0% | 8 hours | 100%
Complete the calculation of the target cost for the solution version | Cost Department | 0% | 152 hours | 100%
16. "Investment Calculation" (Plan) | Finance Department | 0% | 2176 hours | 100%
Sales progress and price expectation in the planning phase | Marketing Department | 0% | 8 hours | 100%
Calculation of Target Cost for the Plan Version | Cost Department | 0% | 8 hours | 100%
17. "Preliminary Design Assignment Document" | R&D | 0% | 40 hours | 100%
Project leader reviews and submits to PMO meeting | Project Leader | 0% | 24 hours | 100%
PMO Meeting Review and Argumentation | PMO | 0% | 16 hours | 100%
Submit for Group Approval | PMO Convenor | 0% | 24 hours | 100%
3. Complete the design plan | R&D Department | 0% | 0 hours | 100%
Propose the "Schematic Product List" and the "Schematic Price Forecast Table" | Marketing Department | 0% | 56 hours | 100%
Determine the project name | Marketing Department | 0% | 56 hours | 100%
Preliminary Design | R&D Department | 0% | 696 hours | 100%
Issue the preliminary design task book | R&D Department | 0% | 40 hours | 100%
Complete preliminary design | R&D Department | 0% | 336 hours | 100%
Municipal Supporting Plan Approval | R&D Department | 0% | 240 hours | 100%
Municipal Supporting Plan Approval | Engineering Department | 0% | 240 hours | 100%
Water Services | R&D Department | 0% | 120 hours | 100%
Water Services | Engineering Department | 0% | 120 hours | 100%
Power Supply | R&D Department | 0% | 120 hours | 100%
Power Supply | Engineering Department | 0% | 120 hours | 100%
Gas | R&D Department | 0% | 120 hours | 100%
Gas | Engineering Department | 0% | 120 hours | 100%
Civil Air Defense | R&D Department | 0% | 240 hours | 100%
Preliminary Design Approval | R&D Department | 0% | 88 hours | 100%
Preliminary Design Results Internal Briefing (Finance, Engineering, Marketing, Cost Procurement) | R&D Department | 0% | 56 hours | 100%
Preliminary Design Outcome Calculation and Construction Guidance | Project Team | 0% | 152 hours | 100%
18. Preliminary Design Results | R&D Department | 0% | 56 hours | 100%
19. "Landscape Design Scheme Results" | R&D Department | 0% | 56 hours | 100%
20. "Luxury Housing Scheme Design Task Book" (if any) | R&D Department | 0% | 56 hours | 100%
21. Investment Calculation and Analysis (Preliminary Design) | Finance Department | 0% | 56 hours | 100%
22. Project Target Cost | Finance Department | 0% | 56 hours | 100%
Target Cost Breakdown | Finance Department | 0% | 56 hours | 100%
23. Project Sales Indicators | Finance Department | 0% | 56 hours | 100%
Project leader reviews and submits to PMO meeting | Project Leader | 0% | 56 hours | 100%
PMO Meeting Review and Argumentation | PMO | 0% | 16 hours | 100%
Submit for Group Approval | PMO Convenor | 0% | 24 hours | 100%
Propose the "Preliminary Design Version Product List" | Marketing Department | 0% | 56 hours | 100%
Propose the "Preliminary Design Version Price Forecast Table" | Marketing Department | 0% | 56 hours | 100%
4. Complete preliminary design | R&D Department | 0% | 0 hours | 100%
Construction Drawing Design | R&D Department | 0% | 2,200 hours | 100%
Geological Exploration | Engineering Department | 0% | 920 hours | 100%
Preliminary Survey | Engineering Department | 0% | 240 hours | 100%
Detailed Exploration | Engineering Department | 0% | 240 hours | 100%
Complete pile layout diagram and foundation construction drawing | R&D Department | 0% | 200 hours | 100%
Complete Construction Drawing Design | R&D Department | 0% | 320 hours | 100%
Construction Drawing Design Document Approval (Reviewing Agency, Lightning Protection Office, Civil Defense Office) | R&D Department | 0% | 80 hours | 100%
Obtain the Construction Engineering Planning Permit | R&D Department | 0% | 160 hours | 100%
Prepare materials | R&D Department | 0% | 24 hours | 100%
Apply for the Construction Engineering Planning Permit | R&D Department | 0% | 160 hours | 100%
Municipal Supporting Specialized Construction Drawing Design | R&D Department | 0% | 984 hours | 100%
Municipal Supporting Plan Design | R&D Department | 0% | 240 hours | 100%
Municipal Supporting Plan Design | Engineering Department | 0% | 240 hours | 100%
Power Supply | R&D Department | 0% | 120 hours | 100%
Power Supply | Engineering Department | 0% | 120 hours | 100%
Gas | R&D Department | 0% | 240 hours | 100%
Gas | Engineering Department | 0% | 240 hours | 100%
Water Supply | R&D Department | 0% | 240 hours | 100%
Water Supply | Engineering Department | 0% | 240 hours | 100%
Communications | R&D Department | 0% | 240 hours | 100%
Communications | Engineering Department | 0% | 240 hours | 100%
Community Integrated Utility Network Map | R&D Department | 0% | 80 hours | 100%
Community Integrated Utility Network Map | Engineering Department | 0% | 80 hours | 100%
Municipal Supporting Construction Drawings | R&D Department | 0% | 240 hours | 100%
Municipal Supporting Construction Drawings | Engineering Department | 0% | 240 hours | 100%
Power Supply | R&D Department | 0% | 240 hours | 100%
Power Supply | Engineering Department | 0% | 240 hours | 100%
Gas | R&D Department | 0% | 240 hours | 100%
Gas | Engineering Department | 0% | 240 hours | 100%
Water Supply | R&D Department | 0% | 240 hours | 100%
Water Supply | Engineering Department | 0% | 240 hours | 100%
Communications | R&D Department | 0% | 240 hours | 100%
Communications | Engineering Department | 0% | 240 hours | 100%
Civil Air Defense | R&D Department | 0% | 320 hours | 100%
Civil Air Defense | Engineering Department | 0% | 320 hours | 100%
Municipal Landscape | R&D Department | 0% | 240 hours | 100%
Municipal Landscape | Engineering Department | 0% | 240 hours | 100%
Municipal Greening Construction Drawing Approval | Engineering Department | 0% | 120 hours | 100%
Riverbank Construction Plan Approval | Engineering Department | 0% | 120 hours | 100%
Construction Drawing Internal Handover | R&D Department | 0% | 80 hours | 100%
5. Complete construction drawing design | R&D Department | 0% | 0 hours | 100%
Propose the "Construction Fence Packaging Plan" | Marketing Department | 0% | 120 hours | 100%
Landscape Design | R&D Department | 0% | 1,080 hours | 100%
Complete the landscape concept design and handover | R&D Department | 0% | 360 hours | 100%
Complete the landscape preliminary design and handover | R&D Department | 0% | 240 hours | 100%
Complete landscape construction drawing design and handover | R&D Department | 0% | 480 hours | 100%
Demonstration Area Design | R&D Department | 0% | 776 hours | 100%
Architectural Design | R&D Department | 0% | 240 hours | 100%
Landscape Design | R&D Department | 0% | 160 hours | 100%
Interior Design | R&D Department | 0% | 536 hours | 100%
Issue the task statement for refined interior design scheme | R&D Department | 0% | 56 hours | 100%
Clubhouse | R&D Department | 0% | 56 hours | 100%
Sample Room | R&D Department | 0% | 56 hours | 100%
Complete the refined decoration plan design and briefing | R&D Department | 0% | 240 hours | 100%
Complete the refined decoration construction drawing design and handover | R&D Department | 0% | 240 hours | 100%
Rough-in Design for Finishing (if applicable) | R&D Department | 0% | 720 hours | 100%
Rough-in Design for Finishing House | R&D Department | 0% | 320 hours | 100%
Rough-in Construction Drawing Design for Finishing Works | R&D Department | 0% | 400 hours | 100%
Guiding System Design | R&D Department | 0% | 560 hours | 100%
Sign the sign system design contract | R&D Department | 0% | 80 hours | 100%
Complete the signage system design and handover | R&D Department | 0% | 480 hours | 100%
Construction Preparation | Engineering Department | 0% | 4,112 hours | 100%
Three Utilities and One Leveling Project | Engineering Department | 0% | 256 hours | 100%
Temporary Water | Engineering Department | 0% | 256 hours | 100%
Linsui Plan | Engineering Department | 0% | 56 hours | 100%
Linsui Contract | Cost Department | 0% | 24 hours | 100%
Linsui Implementation | Engineering Department | 0% | 200 hours | 100%
Temporary Electricity | Engineering Department | 0% | 256 hours | 100%
Temporary Power Supply Plan | Engineering Department | 0% | 56 hours | 100%
Temporary Power Contract | Cost Department | 0% | 24 hours | 100%
Temporary Power Implementation | Engineering Department | 0% | 200 hours | 100%
Temporary Road | Engineering Department | 0% | 256 hours | 100%
Temporary Road Plan | Engineering Department | 0% | 80 hours | 100%
Temporary Road Implementation | Engineering Department | 0% | 2176 hours | 100%
Site Preparation | Engineering Department | 0% | 184 hours | 100%
Site Grading Plan | Engineering Department | 0% | 24 hours | 100%
Site Dredging | Engineering Department | 0% | 160 hours | 100%
Earthwork Balance | Engineering Department | 0% | 160 hours | 100%
Site Survey | Engineering Department | 0% | 200 hours | 100%
Site Survey | Engineering Department | 0% | 360 hours | 100%
Stakeout Nails | Engineering Department | 0% | 80 hours | 100%
Elevation Survey of Site Grid Network | Engineering Department | 0% | 56 hours | 100%
Underground Utility Survey | Engineering Department | 0% | 56 hours | 100%
On-site Temporary Facilities | Engineering Department | 0% | 216 hours | 100%
Temporary Office Housing | Engineering Department | 0% | 216 hours | 100%
Develop an office space plan | Engineering Department | 0% | 56 hours | 100%
Office Room Bidding | Cost Department | 0% | 56 hours | 100%
On-site Office Building Construction | Engineering Department | 0% | 480 hours | 100%
Office building mechanical and electrical installation, network | Engineering Department | 0% | 56 hours | 100%
Temporary Wall Fence | Engineering Department | 0% | 216 hours | 100%
Temporary Fence Plan | R&D Department | 0% | 56 hours | 100%
Temporary Fence Contract | Cost Department | 0% | 24 hours | 100%
Confirming the contractor for the temporary perimeter wall | Cost Department | 0% | 56 hours | 100%
Confirming the contractor for the temporary perimeter wall | Engineering Department | 0% | 56 hours | 100%
Temporary Fence Implementation | Engineering Department | 0% | 80 hours | 100%
Engineering Pre-construction Contract | Cost Department | 0% | 4,112 hours | 100%
General Contracting Contract | Cost Department | 0% | 944 hours | 100%
General Contracting Bidding Zone Division Plan | Engineering Department | 0% | 24 hours | 100%
Cost Consulting Contract Signing | Cost Department | 0% | 240 hours | 100%
Construction Unit Site Inspection | Engineering Department | 0% | 240 hours | 100%
Construction Unit Site Inspection | Cost Department | 0% | 240 hours | 100%
Total Contract Awarding | Cost Department | 0% | 240 hours | 100%
General Contract Signing | Cost Department | 0% | 80 hours | 100%
Supervision Contract | Cost Department | 0% | 144 hours | 100%
Examine the Supervision Unit | Engineering Department | 0% | 80 hours | 100%
Tendering of Supervision Unit | Cost Department | 0% | 40 hours | 100%
Sign the Supervision Contract | Cost Department | 0% | 24 hours | 100%
Earthwork Construction Contract | Cost Department | 0% | 168 hours | 100%
Examine Earthwork Units | Engineering Department | 0% | 112 hours | 100%
Earthwork Construction Bidding | Cost Department | 0% | 40 hours | 100%
Determine Earthwork Construction Contractor | Cost Department | 0% | 16 hours | 100%
Sign the earthwork construction contract | Cost Department | 0% | 16 hours | 100%
Relevant Owner-Supplied Materials/Equipment Contracts | Cost Department | 0% | 1,616 hours | 100%
Sanitary fixtures | Cost Department | 0% | 136 hours | 100%
Sanitary Ware Contract Requirements | Engineering Department | 0% | 56 hours | 100%
Sanitary Ware Contract Signing | Cost Department | 0% | 80 hours | 100%
Exterior Wall Materials | Cost Department | 0% | 136 hours | 100%
Exterior Wall Material Contract Requirements | Engineering Department | 0% | 56 hours | 100%
Exterior Wall Material Contract Signing | Cost Department | 0% | 80 hours | 100%
Nursery Stock Procurement | Cost Department | 0% | 136 hours | 100%
Tree Seedling Procurement Contract Requirement | Engineering Department | 0% | 80 hours | 100%
Signing of Seedling Procurement Contract | Cost Department | 0% | 56 hours | 100%
Specified Subcontracting Contract | Cost Department | 0% | 936 hours | 100%
Weak Electrical System (Perimeter, Surveillance, Patrol, Intercom, Resident Alarm, Fire Protection) | Cost Department | 0% | 320 hours | 100%
Weak Electrical System Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Weak Electrical System Contract Signing | Cost Department | 0% | 240 hours | 100%
Satellite TV | Cost Department | 0% | 320 hours | 100%
Satellite TV Contract Requirements | Cost Department | 0% | 80 hours | 100%
Satellite TV Contract Signing | Cost Department | 0% | 240 hours | 100%
Residential Area Water Feature | Cost Department | 0% | 320 hours | 100%
Neighborhood Water Feature Contract Requirements | Cost Department | 0% | 80 hours | 100%
Neighborhood Water Feature Contract Signing | Cost Department | 0% | 240 hours | 100%
Rough-in Construction Contract | Cost Department | 0% | 800 hours | 100%
Rough Finishing Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Construction Unit Bidding and Tendering | Cost Department | 0% | 80 hours | 100%
Material Confirmation for Renovation | R&D Department | 0% | 160 hours | 100%
Cost Accounting | Cost Department | 0% | 120 hours | 100%
Fine Finishing Contract Signing | Cost Department | 0% | 120 hours | 100%
Rough Finishing (Clubhouse, Model Room) Mechanical and Electrical Installation Contract | Cost Department | 0% | 80 hours | 100%
Air Conditioning System | Cost Department | 0% | 80 hours | 100%
Air Conditioning Contract Requirements | Engineering Department | 0% | 40 hours | 100%
Air Conditioning Contract Signing | Cost Department | 0% | 40 hours | 100%
Floor Heating System | Cost Department | 0% | 80 hours | 100%
Floor Heating Contract Requirements | Engineering Department | 0% | 40 hours | 100%
Floor Heating Contract Signing | Cost Department | 0% | 40 hours | 100%
Landscape | Cost Department | 0% | 1,976 hours | 100%
Landscape Construction Contractor Evaluation | Engineering Department | 0% | 240 hours | 100%
Landscape Construction Contractor Evaluation | Cost Department | 0% | 240 hours | 100%
苗源调查 translates to "Seedling Source Investigation" in English. | Engineering Department | 0% | 240 hours | 100%
苗源调查 translates to "Seedling Source Investigation" in English. | Cost Department | 0% | 240 hours | 100%
Nursery Land Condition Survey | Public Relations Department | 0% | 240 hours | 100%
Nursery Land Condition Survey | Cost Department | 0% | 240 hours | 100%
Nursery Construction | Engineering Department | 0% | 480 hours | 100%
Nursery Construction | Cost Department | 0% | 480 hours | 100%
Landscape Construction Contractor Bidding and Tendering | Cost Department | 0% | 1,120 hours | 100%
Landscape Construction Contractor Bidding and Tendering | Engineering Department | 0% | 1,120 hours | 100%
Landscape Material Selection and Ordering | Cost Department | 0% | 120 hours | 100%
Providing the quantity of hard and soft landscape works | Cost Department | 0% | 120 hours | 100%
Work Quantity Completion List | Cost Department | 0% | 160 hours | 100%
Sign the nursery lease contract | Engineering Department | 0% | 80 hours | 100%
Sign the nursery lease contract | Cost Department | 0% | 80 hours | 100%
Landscape Contract Requirements | Cost Department | 0% | 80 hours | 100%
Landscape Contract Signing | Cost Department | 0% | 120 hours | 100%
Municipal Supporting Contract | Cost Department | 0% | 520 hours | 100%
Natural Gas Installation Contract | Cost Department | 0% | 400 hours | 100%
Natural Gas Installation Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Natural Gas Installation Contract Requirements | Cost Department | 0% | 80 hours | 100%
Natural Gas Installation Contract | Cost Department | 0% | 320 hours | 100%
Water Supply (Including Fire Hydrant) Installation Contract | Cost Department | 0% | 400 hours | 100%
Water Supply Installation Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Water Supply Installation Contract Requirements | Cost Department | 0% | 80 hours | 100%
Water Supply Installation Contract | Cost Department | 0% | 320 hours | 100%
Power Supply System Contract | Cost Department | 0% | 400 hours | 100%
Cable Laying Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Cable Laying Contract Requirements | Cost Department | 0% | 80 hours | 100%
Cable Laying Contract | Cost Department | 0% | 320 hours | 100%
Distribution Room Installation Contract Requirements | Engineering Department | 0% | 80 hours | 100%
Distribution Room Installation Contract Requirements | Cost Department | 0% | 80 hours | 100%
Distribution Room Installation Contract | Cost Department | 0% | 320 hours | 100%
Drainage Inspection Well Contract | Cost Department | 0% | 216 hours | 100%
Drainage Inspection Well Contract Requirements | Engineering Department | 0% | 56 hours | 100%
Drainage Inspection Well Contract Requirements | Cost Department | 0% | 56 hours | 100%
Drainage Inspection Well Contract | Cost Department | 0% | 160 hours | 100%
Telecom (including broadband) contract | Cost Department | 0% | 216 hours | 100%
Telecom (including broadband) contract requirements | Engineering Department | 0% | 56 hours | 100%
Telecom (including broadband) contract requirements | Cost Department | 0% | 56 hours | 100%
Telecom (including broadband) contract | Cost Department | 0% | 160 hours | 100%
Cable TV Contract | Cost Department | 0% | 216 hours | 100%
Cable TV Contract Requirements | Engineering Department | 0% | 56 hours | 100%
Cable TV Contract Requirements | Cost Department | 0% | 56 hours | 100%
Cable TV Contract | Cost Department | 0% | 160 hours | 100%
Construction Permit Processing | Engineering Department | 0% | 400 hours | 100%
Handle bidding and tendering procedures | Engineering Department | 0% | 400 hours | 100%
Preliminary Design and Budget Approval Document | Engineering Department | 0% | 160 hours | 100%
Determining the Tendering Agency | Engineering Department | 0% | 240 hours | 100%
6. Obtain construction permit | Engineering Department | 0% | 0 hours | 100%
Construction Preparation Phase Deliverables | PMO Specialist | 0% | 680 hours | 100%
24. "Construction and Supervision Unit Screening and Evaluation Report" | Engineering Department | 0% | 160 hours | 100%
25. Tendering, Pricing Plan, and Contract Planning | Cost Department | 0% | 160 hours | 100%
26. "Three Utilities and One Leveling Implementation Plan" | Engineering Department | 0% | 160 hours | 100%
27. Project Management Outline | Engineering Department | 0% | 160 hours | 100%
PMO Review | PMO Specialist | 0% | 16 hours | 100%
Submit for Group Approval | PMO Specialist | 0% | 56 hours | 100%
Engineering Implementation | Engineering Department | 0% | 4,888 hours | 100%
7. Project Commencement (Formal) | Engineering Department | 0% | 0 hours | 100%
One Construction Engineering Group Construction | Engineering Department | 0% | 3,416 hours | 100%
Site Handover for Construction | Engineering Department | 0% | 16 hours | 100%
Materials confirmation and price recognition completed | Engineering Department | 0% | 240 hours | 100%
Pile Foundation Engineering | Engineering Department | 0% | 240 hours | 100%
Basic Engineering | Engineering Department | 0% | 240 hours | 100%
Main structure to topping-out status | Engineering Department | 0% | 480 hours | 100%
Roof Engineering | Engineering Department | 0% | 240 hours | 100%
Masonry Work | Engineering Department | 0% | 240 hours | 100%
Interior Engineering | Engineering Department | 0% | 240 hours | 100%
Interior plastering | Engineering Department | 0% | 240 hours | 100%
Exterior Engineering Project | Engineering Department | 0% | 1,816 hours | 100%
Exterior Painting | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Insulation | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Cladding | Engineering Department | 0% | 360 hours | 100%
Equipment Installation Engineering | Engineering Department | 0% | 400 hours | 100%
Structure topping off to sellable condition | Engineering Department | 0% | 0 hours | 100%
Exterior construction completed and all external scaffolding removed (in phases) | Engineering Department | 0% | 480 hours | 100%
Two Group Engineering Construction | Engineering Department | 0% | 3,176 hours | 100%
Pile Foundation Engineering | Engineering Department | 0% | 240 hours | 100%
Basic Engineering | Engineering Department | 0% | 240 hours | 100%
Main structure to topping-out status | Engineering Department | 0% | 480 hours | 100%
Roof Engineering | Engineering Department | 0% | 240 hours | 100%
Masonry Work | Engineering Department | 0% | 240 hours | 100%
Interior Engineering | Engineering Department | 0% | 240 hours | 100%
Interior plastering | Engineering Department | 0% | 240 hours | 100%
Exterior Engineering Project | Engineering Department | 0% | 1,576 hours | 100%
Exterior Painting | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Insulation | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Cladding | Engineering Department | 0% | 360 hours | 100%
Equipment Installation Engineering | Engineering Department | 0% | 400 hours | 100%
Structure topping off to sellable condition | Engineering Department | 0% | 0 hours | 100%
Exterior construction completed and all external scaffolding removed (in phases) | Engineering Department | 0% | 240 hours | 100%
Three Group Engineering Construction | Engineering Department | 0% | 2,936 hours | 100%
Pile Foundation Engineering | Engineering Department | 0% | 240 hours | 100%
Basic Engineering | Engineering Department | 0% | 240 hours | 100%
Main structure to topping-out status | Engineering Department | 0% | 480 hours | 100%
Roof Engineering | Engineering Department | 0% | 240 hours | 100%
Masonry Work | Engineering Department | 0% | 240 hours | 100%
Interior Engineering | Engineering Department | 0% | 240 hours | 100%
Interior plastering | Engineering Department | 0% | 240 hours | 100%
Exterior Engineering Project | Engineering Department | 0% | 1,240 hours | 100%
Exterior Painting | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Insulation | Engineering Department | 0% | 240 hours | 100%
Exterior Wall Cladding | Engineering Department | 0% | 360 hours | 100%
Equipment Installation Engineering | Engineering Department | 0% | 400 hours | 100%
Structure topping off to sellable condition | Engineering Department | 0% | 0 hours | 100%
Exterior construction completed and all external scaffolding removed (in phases) | Engineering Department | 0% | 240 hours | 100%
Municipal Facilities Construction Commencement | Engineering Department | 0% | 720 hours | 100%
Municipal Infrastructure Construction (Phased) | Engineering Department | 0% | 720 hours | 100%
Landscape Greening Construction | Engineering Department | 0% | 1,168 hours | 100%
Handle Supervision Reporting | Engineering Department | 0% | 16 hours | 100%
Soil Testing | Engineering Department | 0% | 56 hours | 100%
Landscape Construction Drawing Handover | R&D Department | 0% | 56 hours | 100%
On-site Construction | Engineering Department | 0% | 720 hours | 100%
Comment | Engineering Department | 0% | 8 hours | 100%
Comment | R&D Department | 0% | 8 hours | 100%
Comment | Marketing Department | 0% | 8 hours | 100%
Comment | Cost Department | 0% | 8 hours | 100%
Effect Adjustment | Engineering Department | 0% | 56 hours | 100%
Effect Adjustment | R&D Department | 0% | 56 hours | 100%
Effect Adjustment | Marketing Department | 0% | 56 hours | 100%
Effect Adjustment | Cost Department | 0% | 56 hours | 100%
Work cleanup completed | Engineering Department | 0% | 56 hours | 100%
Check and Rectification | Engineering Department | 0% | 80 hours | 100%
8. Landscape Construction Commencement | Engineering Department | 0% | 0 hours | 100%
Engineering Completion | Engineering Department | 0% | 1,040 hours | 100%
Epidemic Prevention and Control | Engineering Department | 0% | 40 hours | 100%
Drinking Water Quality Terminal Testing | Engineering Department | 0% | 16 hours | 100%
Health and Epidemic Prevention Acceptance Report | Engineering Department | 0% | 24 hours | 100%
Lightning protection inspection | Engineering Department | 0% | 88 hours | 100%
Lightning protection inspection | Engineering Department | 0% | 40 hours | 100%
Lightning protection inspection report | Engineering Department | 0% | 48 hours | 100%
Environmental Protection Acceptance | Engineering Department | 0% | 96 hours | 100%
Environmental Protection Testing | Engineering Department | 0% | 32 hours | 100%
Environmental Protection Inspection Report | Engineering Department | 0% | 48 hours | 100%
Planning Acceptance | Engineering Department | 0% | 120 hours | 100%
Planning Inspection (Line Check) | Engineering Department | 0% | 40 hours | 100%
Planning Inspection Report | Engineering Department | 0% | 40 hours | 100%
Fire Acceptance | Engineering Department | 0% | 88 hours | 100%
Fire inspection | Engineering Department | 0% | 16 hours | 100%
Fire Acceptance Report | Engineering Department | 0% | 48 hours | 100%
Security Acceptance | Engineering Department | 0% | 240 hours | 100%
Technical Prevention Testing | Engineering Department | 0% | 120 hours | 100%
Technical Prevention Acceptance Report | Engineering Department | 0% | 80 hours | 100%
Technical Supervision Bureau Acceptance (Elevator) | Engineering Department | 0% | 80 hours | 100%
Civil Air Defense Acceptance | Engineering Department | 0% | 40 hours | 100%
Archive Acceptance | Engineering Department | 0% | 56 hours | 100%
Indoor Air Quality Testing | Engineering Department | 0% | 40 hours | 100%
Municipal Facilities Acceptance | Engineering Department | 0% | 480 hours | 100%
Water Supply Acceptance and Obtaining Supporting Certifications | Engineering Department | 0% | 160 hours | 100%
Power supply acceptance and obtaining supporting certificates | Engineering Department | 0% | 480 hours | 100%
High-voltage section acceptance | Engineering Department | 0% | 120 hours | 100%
Low-voltage Section Acceptance | Engineering Department | 0% | 120 hours | 100%
Formal Power Supply | Engineering Department | 0% | 160 hours | 100%
Issue supporting documents | Engineering Department | 0% | 160 hours | 100%
Gas acceptance and obtaining supporting documents | Engineering Department | 0% | 400 hours | 100%
Pressure Regulating Station Acceptance | Engineering Department | 0% | 40 hours | 100%
Foreign Management Acceptance | Engineering Department | 0% | 160 hours | 100%
Internal Management Acceptance | Engineering Department | 0% | 120 hours | 100%
Formal Air Supply | Engineering Department | 0% | 16 hours | 100%
Issue supporting documents | Engineering Department | 0% | 160 hours | 100%
Drainage Acceptance and Obtaining Supporting Certifications | Engineering Department | 0% | 160 hours | 100%
Communication Acceptance and Obtaining Supporting Documents | Engineering Department | 0% | 160 hours | 100%
Cable TV Acceptance and Obtaining Supporting Documentation | Engineering Department | 0% | 160 hours | 100%
Greening Acceptance | Engineering Department | 0% | 40 hours | 100%
Wall Acceptance Inspection | Engineering Department | 0% | 40 hours | 100%
Comprehensive Acceptance | Engineering Department | 0% | 24 hours | 100%
Completion Filing | Engineering Department | 0% | 480 hours | 100%
Completion Documents | Engineering Department | 0% | 480 hours | 100%
Entity Acceptance | Engineering Department | 0% | 8 hours | 100%
9. Completion Filing | Engineering Department | 0% | 0 hours | 100%
Pre-transfer inspection and rectification | Engineering Department | 0% | 240 hours | 100%
Construction of clubhouse (on-site sales office) and demonstration area | Engineering Department | 0% | 1,408 hours | 100%
Main Structure Construction | Engineering Department | 0% | 1,232 hours | 100%
Site Handover for Construction | Engineering Department | 0% | 32 hours | 100%
Materials confirmation and price recognition completed | Cost Department | 0% | 120 hours | 100%
Implementation and Confirmation of Renovation Samples | Engineering Department | 0% | 120 hours | 100%
Pile Foundation Engineering | Engineering Department | 0% | 200 hours | 100%
Basic Engineering | Engineering Department | 0% | 160 hours | 100%
Main structure to topping-out status | Engineering Department | 0% | 400 hours | 100%
Roof Engineering | Engineering Department | 0% | 200 hours | 100%
Masonry Work | Engineering Department | 0% | 200 hours | 100%
Interior Engineering | Engineering Department | 0% | 160 hours | 100%
Interior plastering | Engineering Department | 0% | 160 hours | 100%
Exterior Engineering Project | Engineering Department | 0% | 928 hours | 100%
Exterior Painting | Engineering Department | 0% | 120 hours | 100%
Exterior Wall Insulation | Engineering Department | 0% | 120 hours | 100%
Exterior Wall Cladding | Engineering Department | 0% | 240 hours | 100%
Equipment Installation Engineering | Engineering Department | 0% | 720 hours | 100%
Structure topping off to sellable condition | Engineering Department | 0% | 0 hours | 100%
Exterior construction completed and all external scaffolding removed (in phases) | Engineering Department | 0% | 120 hours | 100%
Lobby Refined Renovation | Engineering Department | 0% | 800 hours | 100%
Site Handover for Construction | Engineering Department | 0% | 24 hours | 100%
Materials confirmation and price recognition completed | Cost Department | 0% | 80 hours | 100%
Implementation and Confirmation of Renovation Samples | Engineering Department | 0% | 160 hours | 100%
Interior Construction | Engineering Department | 0% | 560 hours | 100%
Sales Office Interior Renovation | Engineering Department | 0% | 800 hours | 100%
Site Handover for Construction | Engineering Department | 0% | 24 hours | 100%
Materials confirmation and price recognition completed | Cost Department | 0% | 80 hours | 100%
Implementation and Confirmation of Renovation Samples | Engineering Department | 0% | 160 hours | 100%
Interior Construction | Engineering Department | 0% | 560 hours | 100%
Sample Room Finishing | Engineering Department | 0% | 800 hours | 100%
Site Handover for Construction | Engineering Department | 0% | 24 hours | 100%
Materials confirmation and price recognition completed | Cost Department | 0% | 80 hours | 100%
Implementation and Confirmation of Renovation Samples | Engineering Department | 0% | 160 hours | 100%
Interior Construction | Engineering Department | 0% | 560 hours | 100%
Soft furnishing and placement of decorations | Marketing Department | 0% | 240 hours | 100%
Site Handover | Engineering Department | 0% | 16 hours | 100%
Materials confirmation and price recognition completed | Cost Department | 0% | 24 hours | 100%
Implementation and Confirmation of Decorative Samples | Marketing Department | 0% | 120 hours | 100%
Decorative Construction | Marketing Department | 0% | 120 hours | 100%
Items Arrangement and Cleaning | Marketing Department | 0% | 56 hours | 100%
Greening and landscape construction outside the demonstration area | Engineering Department | 0% | 848 hours | 100%
10. Clubhouse (on-site sales office) and demonstration area opening | Project Team | 0% | 8 hours | 100%
Marketing | Marketing Department | 0% | 6,136 hours | 100%
Demo Area and Sales Office | Marketing Department | 0% | 2,280 hours | 100%
Sales Office (Outdoor) | Marketing Department | 0% | 992 hours | 100%
Field Sales Office Site Selection | Marketing Department | 0% | 240 hours | 100%
Field Sales Office Design | Marketing Department | 0% | 360 hours | 100%
Field Sales Office Construction and Arrangement | Marketing Department | 0% | 360 hours | 100%
Develop the Management Method for Off-site Sales Office | Marketing Department | 0% | 96 hours | 100%
Compile the on-site sales office reception process | Marketing Department | 0% | 96 hours | 100%
Property service staff in place | Property Department | 0% | 40 hours | 100%
Sales Office Opening (Field) | Marketing Department | 0% | 8 hours | 100%
Sales Office and Model Unit on Site | Marketing Department | 0% | 1,016 hours | 100%
Demo Area Scenario Layout Plan | Marketing Department | 0% | 240 hours | 100%
Scenario Creation for Demonstration Area | Marketing Department | 0% | 240 hours | 100%
Sales Office Handover | Marketing Department | 0% | 40 hours | 100%
Sales Office and Model Room Material Arrangement | Marketing Department | 0% | 120 hours | 100%
Sales Office Contract Printing Equipment Purchase | Marketing Department | 0% | 16 hours | 100%
Sales Office Equipment Procurement | Marketing Department | 0% | 80 hours | 100%
Sales Office Equipment and Facilities Arrangement | Marketing Department | 0% | 16 hours | 100%
Sales Office Promotion Material Arrangement | Marketing Department | 0% | 16 hours | 100%
Prepare Sales Office and Model Room Management Regulations | Marketing Department | 0% | 96 hours | 100%
Compile sales office and model unit reception procedures | Marketing Department | 0% | 96 hours | 100%
Property service staff in place | Marketing Department | 0% | 24 hours | 100%
Property Company Bidding and Preparation of Pre-property Documents | General Manager | 0% | 480 hours | 100%
Marketing Strategy Plan | Marketing Department | 0% | 2,232 hours | 100%
Selection of Advertising Company | Marketing Department | 0% | 240 hours | 100%
Determine the overall promotion strategy plan | Marketing Department | 0% | 200 hours | 100%
Marketing Channel Expansion and Integration | Marketing Department | 0% | 720 hours | 100%
Determine the project name, promotional slogan, and logo | Marketing Department | 0% | 160 hours | 100%
Determine the series of advertisements, outdoor advertising | Marketing Department | 0% | 160 hours | 100%
Develop (Preheating Period) Media Plan | Marketing Department | 0% | 160 hours | 100%
Develop (Strong Sales Period, Sustained Period) Media Plan | Marketing Department | 0% | 80 hours | 100%
Prop Preparation | Marketing Department | 0% | 2,760 hours | 100%
Basic Information | Marketing Department | 0% | 2,760 hours | 100%
Render the visual effect drawing | Marketing Department | 0% | 488 hours | 100%
Provide furniture layout diagrams for unit types before and after integration | R&D Department | 0% | 8 hours | 100%
Determine the rendering style | Marketing Department | 0% | 80 hours | 100%
Rendered Effect Image | Marketing Department | 0% | 240 hours | 100%
Sample Area, Sample Room Photography | Marketing Department | 0% | 168 hours | 100%
Sample Area and Model Room Photography Plan | Marketing Department | 0% | 40 hours | 100%
Sample Area Model Room Photography | Marketing Department | 0% | 120 hours | 100%
Map | Marketing Department | 0% | 456 hours | 100%
Map Information Collection | Marketing Department | 0% | 80 hours | 100%
Map Drawing | Marketing Department | 0% | 80 hours | 100%
Sales Announcement Materials | Marketing Department | 0% | 360 hours | 100%
Publicity License | Marketing Department | 0% | 56 hours | 100%
"Presale/Sales Contract Configuration Standards" | Marketing Department | 0% | 56 hours | 100%
"Pre-sale/Sales Contract Appendix" | Marketing Department | 0% | 56 hours | 100%
Deposit Contract Template | Marketing Department | 0% | 56 hours | 100%
"Model Sales/Purchase Contract" | Marketing Department | 0% | 56 hours | 100%
"Supplementary Agreement for Presale/Sale Contract" | Marketing Department | 0% | 56 hours | 100%
《Home Purchase Process》 | Marketing Department | 0% | 8 hours | 100%
"Home Purchase Guidelines" and "Payment Guidelines" | Marketing Department | 0% | 240 hours | 100%
Risk Disclosure | Marketing Department | 0% | 240 hours | 100%
Public display version, public display rack production | Marketing Department | 0% | 80 hours | 100%
Website creation and publication | Marketing Department | 0% | 688 hours | 100%
Prepare related images and text | Marketing Department | 0% | 80 hours | 100%
Website Development Company Confirmed | Marketing Department | 0% | 160 hours | 100%
Determine the overall content framework of the website | Marketing Department | 0% | 40 hours | 100%
Determine website style | Marketing Department | 0% | 120 hours | 100%
Page design and website setup | Marketing Department | 0% | 240 hours | 100%
Website Launch | Marketing Department | 0% | 8 hours | 100%
Multimedia Production | Marketing Department | 0% | 544 hours | 100%
Multimedia Concept Design Plan | Marketing Department | 0% | 240 hours | 100%
Multimedia design completed | Marketing Department | 0% | 240 hours | 100%
Multimedia Batch Production | Marketing Department | 0% | 56 hours | 100%
Film and Television | Marketing Department | 0% | 480 hours | 100%
Film Script Design | Marketing Department | 0% | 240 hours | 100%
Film Production | Marketing Department | 0% | 240 hours | 100%
Text Materials | Marketing Department | 0% | 2,280 hours | 100%
Apartment Layout Design and Production | Marketing Department | 0% | 304 hours | 100%
Internal Review and Confirmation of Unit Floor Plans | Marketing Department | 0% | 40 hours | 100%
Unit Plan Printing Page Design | Marketing Department | 0% | 208 hours | 100%
Printing completed | Marketing Department | 0% | 40 hours | 100%
Poster (Simple Building Guide) Design and Production | Marketing Department | 0% | 472 hours | 100%
Poster (Simple Building Guide) Concept Design Scheme | Marketing Department | 0% | 160 hours | 100%
The product standards listed in the poster (simple building brochure) are reviewed and confirmed. | Marketing Department | 0% | 40 hours | 100%
Poster (Simple Building Guide) Design Completed | Marketing Department | 0% | 208 hours | 100%
Poster (Simple Building Book) Printing Completed | Marketing Department | 0% | 40 hours | 100%
Building Book Design and Production | Marketing Department | 0% | 600 hours | 100%
Concept Design of Building Brochure | Marketing Department | 0% | 240 hours | 100%
Sign-off and confirmation of product standards listed in the building brochure | Marketing Department | 0% | 40 hours | 100%
Completion of Building Book Design | Marketing Department | 0% | 240 hours | 100%
The completion of building brochure printing | Marketing Department | 0% | 56 hours | 100%
Purchase Guide Compilation, Design, and Production | Marketing Department | 0% | 568 hours | 100%
Purchase Guide Compilation | Marketing Department | 0% | 160 hours | 100%
Purchase Notice Compilation and Co-signing Confirmation | Marketing Department | 0% | 40 hours | 100%
Design of Home Buying Guidelines Completed | Marketing Department | 0% | 240 hours | 100%
The printing of home-buying guidelines has been completed. | Marketing Department | 0% | 56 hours | 100%
Materials | Marketing Department | 0% | 1,720 hours | 100%
Model | Marketing Department | 0% | 1,720 hours | 100%
Model (Field Sales Office) | Marketing Department | 0% | 432 hours | 100%
Provide planning proposal, landscape proposal, and overall site plan, as well as electronic files of individual floor plans, elevations, and sections. | R&D Department | 0% | 8 hours | 100%
Model Company Selection and Scheme Communication | Marketing Department | 0% | 160 hours | 100%
Technical disclosure and monitoring | R&D Department | 0% | 280 hours | 100%
Model Production and Installation | Marketing Department | 0% | 240 hours | 100%
Model (On-site Sales Office) | Marketing Department | 0% | 392 hours | 100%
Model Company Selection and Scheme Communication | Marketing Department | 0% | 160 hours | 100%
Technical disclosure and monitoring | R&D Department | 0% | 240 hours | 100%
Model Production and Installation | Marketing Department | 0% | 240 hours | 100%
Signage System Design and Production | Marketing Department | 0% | 1,616 hours | 100%
Sales Office Signage System Design and Production | Marketing Department | 0% | 328 hours | 100%
Field Sales Office Signage System Layout Plan | Marketing Department | 0% | 80 hours | 100%
Sales Office Signage System Design and Production | Marketing Department | 0% | 240 hours | 100%
On-site Sales Office and Demonstration Area Signage System Design and Production | Marketing Department | 0% | 648 hours | 100%
On-site Sales Office and Demonstration Area Signage System Layout Plan | Marketing Department | 0% | 240 hours | 100%
On-site Sales Office and Demonstration Area Signage System Design and Production | Marketing Department | 0% | 400 hours | 100%
Property Consultant Uniform | Marketing Department | 0% | 320 hours | 100%
Clothing selection and contact with manufacturers | Marketing Department | 0% | 160 hours | 100%
Clothing Production | Marketing Department | 0% | 160 hours | 100%
Name card, Name badge | Marketing Department | 0% | 208 hours | 100%
Name card, name badge design | Marketing Department | 0% | 120 hours | 100%
Name cards, chest badges production | Marketing Department | 0% | 80 hours | 100%
Advertising and Promotion | Marketing Department | 0% | 3,320 hours | 100%
Outdoor Advertising | Marketing Department | 0% | 4,960 hours | 100%
Surrounding Road Signage | Marketing Department | 0% | 4,536 hours | 100%
Peripheral Road Signage Site Selection | Marketing Department | 0% | 496 hours | 100%
Surrounding Road Signage Location Announcement | Marketing Department | 0% | 3,800 hours | 100%
Key traffic route outdoor placement | Marketing Department | 0% | 4,240 hours | 100%
Key transportation route outdoor site selection | Marketing Department | 0% | 1,200 hours | 100%
Key Transportation Route Outdoor Site Selection Announcement | Marketing Department | 0% | 2,800 hours | 100%
Online Advertising | Marketing Department | 0% | 3,600 hours | 100%
Network Advertising Space and Time Slot Booking | Marketing Department | 0% | 3,600 hours | 100%
Network Advertising Design and Publication | Marketing Department | 0% | 3,360 hours | 100%
Newspaper Advertisement | Marketing Department | 0% | 2,640 hours | 100%
Newspaper Ad Slot and Time Booking | Marketing Department | 0% | 2,400 hours | 100%
Newspaper Design and Publication | Marketing Department | 0% | 2,400 hours | 100%
Magazine Advertisement | Marketing Department | 0% | 3,920 hours | 100%
Magazine Ad Space and Time Slot Booking | Marketing Department | 0% | 3,680 hours | 100%
Magazine Advertisement Design and Publication | Marketing Department | 0% | 3,680 hours | 100%
Television advertisement | Marketing Department | 0% | 2,456 hours | 100%
TV Commercial Script Creativity and Production | Marketing Department | 0% | 320 hours | 100%
Television Advertising Booking | Marketing Department | 0% | 296 hours | 100%
Television Advertising Release | Marketing Department | 0% | 2,000 hours | 100%
Radio Advertisement | Marketing Department | 0% | 2,232 hours | 100%
Radio script creativity and production | Marketing Department | 0% | 240 hours | 100%
Radio Advertising Booking | Marketing Department | 0% | 1,760 hours | 100%
Radio Advertisement Release | Marketing Department | 0% | 2,000 hours | 100%
Address Database Advertisement | Marketing Department | 0% | 3,360 hours | 100%
Address Database Selection and Vendor Communication | Marketing Department | 0% | 2,400 hours | 100%
Address Database Advertisement Release | Marketing Department | 0% | 3,200 hours | 100%
Public Relations Activities | Marketing Department | 0% | 664 hours | 100%
Sample Area Opening Event | Marketing Department | 0% | 392 hours | 100%
Activity Theme and Plan Planning | Marketing Department | 0% | 80 hours | 100%
Public Relations Company Proposal | Marketing Department | 0% | 160 hours | 100%
Activity-related Preparation | Marketing Department | 0% | 240 hours | 100%
Activity Implementation | Marketing Department | 0% | 0 hours | 100%
Opening Event | Marketing Department | 0% | 664 hours | 100%
Activity Theme and Plan Planning | Marketing Department | 0% | 160 hours | 100%
Public Relations Company Proposal | Marketing Department | 0% | 160 hours | 100%
Activity-related Preparation | Marketing Department | 0% | 320 hours | 100%
Activity Implementation | Marketing Department | 0% | 0 hours | 100%
Sales Training | Marketing Department | 0% | 1,896 hours | 100%
Sales Consultant in Place | Marketing Department | 0% | 240 hours | 100%
Market Research | Marketing Department | 0% | 120 hours | 100%
Compile Sales Training Materials | Marketing Department | 0% | 1,720 hours | 100%
Standard Sales Training | Marketing Department | 0% | 240 hours | 100%
Sales pitch for property types | Marketing Department | 0% | 80 hours | 100%
Model Explanation | Marketing Department | 0% | 40 hours | 100%
Spokescript for the Demonstration Area | Marketing Department | 0% | 80 hours | 100%
Visit Route Plan | Marketing Department | 0% | 40 hours | 100%
Sales Training | Marketing Department | 0% | 480 hours | 100%
Sales Supporting Organization Confirmation | Finance Department | 0% | 440 hours | 100%
Selection and confirmation of loan banks | Finance Department | 0% | 400 hours | 100%
Loan Bank Training | Finance Department | 0% | 24 hours | 100%
Selection and Confirmation of Notary Office | Finance Department | 0% | 160 hours | 100%
Notary Office Training | Finance Department | 0% | 8 hours | 100%
Public | Marketing Department | 0% | 1,520 hours | 100%
Appearance | Marketing Department | 0% | 0 hours | 100%
Sales Office Opening (Field) | Marketing Department | 0% | 8 hours | 100%
On-site Sales Office Opening | Marketing Department | 0% | 8 hours | 100%
On-site Demonstration Area Opening | Marketing Department | 0% | 8 hours | 100%
Pre-sale Permit Processing | Marketing Department | 0% | 3,568 hours | 100%
Retrieve the company security key | Marketing Department | 0% | 240 hours | 100%
Land Name Application | Marketing Department | 0% | 240 hours | 100%
Application for Door Number | Marketing Department | 0% | 240 hours | 100%
New Construction Start Registration | Marketing Department | 0% | 240 hours | 100%
Enterprise Certification | Marketing Department | 0% | 240 hours | 100%
Project Certification | Marketing Department | 0% | 240 hours | 100%
Surveying and Mapping | Marketing Department | 0% | 480 hours | 100%
Construction Plan Submission | Engineering Department | 0% | 8 hours | 100%
Construction Plan Approval | Engineering Department | 0% | 8 hours | 100%
Supporting Plan Submission | Engineering Department | 0% | 8 hours | 100%
Supporting Plan Approval | Engineering Department | 0% | 8 hours | 100%
Application (Demonstration Area) Pre-sale Permit Pre-sale Permit | Marketing Department | 0% | 616 hours | 100%
On-site Attestation Report (Demonstration Area) | Marketing Department | 0% | 24 hours | 100%
Shanghai Commercial Housing Pre-sale Project Status Table | Marketing Department | 0% | 24 hours | 100%
Real Estate Development Enterprise Qualification Certificate | Administration Department | 0% | 8 hours | 100%
Land Use Right Transfer Contract | Development Department | 0% | 8 hours | 100%
Real Estate Ownership Certificate | Development Department | 0% | 8 hours | 100%
Construction Engineering Planning Permit | R&D Department | 0% | 8 hours | 100%
Construction Engineering Construction Permit | Engineering Department | 0% | 8 hours | 100%
An engineering progress certification report issued by a qualified surveying institution | Engineering Department | 0% | 24 hours | 100%
Construction Area Survey Detail Table (Preliminary Measured Area Survey Results Report) | Marketing Department | 0% | 8 hours | 100%
Agreement for the supervision of pre-sale funds with the institution responsible for fund supervision of real estate projects in this city | Finance Department | 0% | 8 hours | 100%
Pre-sale Plan for Commercial Housing (including sales personnel position certificates and commitment letters, sales prices, and price fluctuation ranges) | Marketing Department | 0% | 80 hours | 100%
Proof that supporting facilities such as water, electricity, and coal have been secured | Engineering Department | 0% | 8 hours | 100%
House Usage Convention | Property Department | 0% | 8 hours | 100%
Pre-construction Property Bidding Certificate and the Pre-construction Property Management Service Contract Signed with the Appointed Property Management Company | Property Department | 0% | 8 hours | 100%
Property Management and Homeowners' Committee Office Configuration Information | Property Department | 0% | 8 hours | 100%
Property Management Company's Qualification Certificate | Property Department | 0% | 8 hours | 100%
Residential Commercial Building Master Plan | R&D Department | 0% | 24 hours | 100%
Apply for the Pre-sale Permit | Marketing Department | 0% | 120 hours | 100%
Application (First Batch of Housing Units) Pre-sale Permit Pre-sale Permit | Marketing Department | 0% | 688 hours | 100%
On-site Attestation Report (First Batch of Housing Units) | Marketing Department | 0% | 24 hours | 100%
Shanghai Commercial Housing Pre-sale Project Status Table | Marketing Department | 0% | 24 hours | 100%
Real Estate Development Enterprise Qualification Certificate | Administration Department | 0% | 8 hours | 100%
Land Use Right Transfer Contract | Development Department | 0% | 8 hours | 100%
Real Estate Ownership Certificate | Development Department | 0% | 8 hours | 100%
Construction Engineering Planning Permit | Engineering Department | 0% | 8 hours | 100%
Construction Engineering Construction Permit | Marketing Department | 0% | 8 hours | 100%
An engineering progress certification report issued by a qualified surveying institution | Marketing Department | 0% | 8 hours | 100%
Construction Area Survey Detail Table (Preliminary Measured Area Survey Results Report) | Marketing Department | 0% | 8 hours | 100%
Agreement for the supervision of pre-sale funds with the institution responsible for fund supervision of real estate projects in this city | Finance Department | 0% | 16 hours | 100%
Pre-sale Plan for Commercial Housing (including sales personnel position certificates and commitment letters, sales prices, and price fluctuation ranges) | Marketing Department | 0% | 80 hours | 100%
Proof that supporting facilities such as water, electricity, and coal have been secured | Engineering Department | 0% | 8 hours | 100%
House Usage Convention | Property Department | 0% | 8 hours | 100%
Pre-construction Property Bidding Certificate and the Pre-construction Property Management Service Contract Signed with the Appointed Property Management Company | Property Department | 0% | 8 hours | 100%
Property Management and Homeowners' Committee Office Configuration Information | Property Department | 0% | 8 hours | 100%
Property Management Company's Qualification Certificate | Property Department | 0% | 8 hours | 100%
Residential Commercial Building Master Plan | R&D Department | 0% | 24 hours | 100%
Apply for the Pre-sale Permit | Marketing Department | 0% | 120 hours | 100%
11. Obtain the pre-sale permit | Marketing Department | 0% | 24 hours | 100%
Cancel Bank Mortgage Rights | Finance Department | 0% | 24 hours | 100%
List property for sale/rent | Marketing Department | 0% | 24 hours | 100%
Marketing Opening Phase Achievements | Project Team | 0% | 344 hours | 100%
28. Marketing Strategy Plan | Marketing Department | 0% | 240 hours | 100%
29. "Sales Contract Configuration Standards" | Marketing Department | 0% | 120 hours | 100%
30. "Contract Appendix Drawing" | Marketing Department | 0% | 240 hours | 100%
31. Price List and Payment Method | Marketing Department | 0% | 56 hours | 100%
Project leader reviews and submits to PMO meeting | Project Leader | 0% | 8 hours | 100%
PMO Meeting Review and Argumentation | PMO | 0% | 8 hours | 100%
Submit for Group Approval | PMO Convenor | 0% | 8 hours | 100%
12. First Opening | Marketing Department | 0% | 8 hours | 100%
Second Opening | Marketing Department | 0% | 8 hours | 100%
Third Opening | Marketing Department | 0% | 8 hours | 100%
Fourth Opening | Marketing Department | 0% | 8 hours | 100%
Handover Phase | Engineering Department | 0% | 1,680 hours | 100%
Complete Property Handover | Engineering Department | 0% | 160 hours | 100%
Handover Preparation | Marketing Department | 0% | 1,448 hours | 100%
Measure property area and land area | Marketing Department | 0% | 440 hours | 100%
Establish a housing delivery preparation team and hold a housing delivery preparation meeting | Marketing Department | 0% | 8 hours | 100%
Implement key control nodes of various departments before delivery, and determine the concentrated delivery period | Marketing Department | 0% | 8 hours | 100%
Identify customer-sensitive issues and propose solutions | Marketing Department | 0% | 640 hours | 100%
Handover Event Preparation | Marketing Department | 0% | 400 hours | 100%
Organize each department to handle customer reports and monitor the processing results | Marketing Department | 0% | 640 hours | 100%
Site Open Day Preparation | Marketing Department | 0% | 200 hours | 100%
Open Site Day | Project Team | 0% | 16 hours | 100%
Problem Rectification | Engineering Department | 0% | 200 hours | 100%
Residential Quality Guarantee Book and Residential User Manual Compilation, Design and Production | Marketing Department | 0% | 200 hours | 100%
Handover Site Arrangement | Marketing Department | 0% | 16 hours | 100%
Handover Training, Staff Arrangement | Marketing Department | 0% | 40 hours | 100%
Deliverable Results at Handover Stage | Project Team | 0% | 360 hours | 100%
32. "Handover Plan" | Marketing Department | 0% | 240 hours | 100%
33. "Commercial Handover Plan" | Commercial Operation Company | 0% | 240 hours | 100%
34. Asset Management Plan | Finance Department | 0% | 240 hours | 100%
Project leader reviews and submits to PMO meeting | Project Leader | 0% | 8 hours | 100%
PMO Meeting Review and Argumentation | PMO | 0% | 8 hours | 100%
Submit for Group Approval | PMO Convenor | 0% | 24 hours | 100%
13. Delivery of housing | Marketing Department | 0% | 0 hours | 100%
14. Delivery completion 95% | Marketing Department | 0% | 240 hours | 100%
Post-Delivery Phase | Project Team | 0% | 288 hours | 100%
Project Subsequent Results | Project Team | 0% | 288 hours | 100%
35. Project Post-Evaluation | PMO | 0% | 240 hours | 100%
Post-Project Evaluation Report Meeting | PMO | 0% | 16 hours | 100%
Submit for Group Approval | PMO Convenor | 0% | 32 hours | 100%